## Sheet1
Trivenisarees Project Proposal - Format
S. No. | Head | Element | Time (In Days) | Cost (INR) | Notes (If anything Specific)
1 | Generic | Site Architecture | CMS Feature
2 |  | Photoshop Design | 10
3 |  | HTML | 10
4 |  | Content/Copy Development | TBD by Client
5 | Back-end | Categories(add, edit, delete, show, add attribute, edit attribute, description, banners) | CMS Feature
6 |  | Collection Under Categories | CMS Feature
7 |  | Add Products | CMS Feature
8 |  | Manage Productwise Inventory | CMS Feature
9 |  | Import Export Products | CMS Feature
10 |  | Review Order, Change Status | CMS Feature
11 |  | Import Export Orders | CMS Feature
12 |  | Coupon Management | CMS Feature
13 |  | Discount System | CMS Feature
14 |  | User Management | CMS Feature
15 |  | Currency Manager | 1
16 |  | Shiping Method by country | 2
17 |  | Transactional Emails | 4
19 |  | Banner Management | CMS Feature
20 |  | Featured Products Management | CMS Feature
21 | Front-end | Homepage | 2
22 |  | Category Page: Filters | CMS Feature
23 |  | Category Page: Infinite Page with Lazy loading | CMS Feature
24 |  | Category Page: Add to cart, wishlist directly | CMS Feature
25 |  | Category Page: Collection and Product View | CMS Feature
26 |  | Category Page: Image zoom feature | CMS Feature
27 |  | Product Page: breadcrumbs | CMS Feature
28 |  | Product Page: Details, Images | CMS Feature
29 |  | Product Page: Add to favourite, Social media links | CMS Feature
30 |  | Product Page: Enquiry Module | CMS Feature
31 |  | Product Page: Custom Options | CMS Feature
32 |  | Product Page: Related Products | CMS Feature
33 |  | Product Page: HTML Integrate | 2
34 |  | Cart Page: HTML Integrate | 2
35 |  | Cart Page: Add, edit, delete | CMS Feature
36 |  | Cart Page: Edit Custom Options | 1
37 |  | Checkout: Integrate HTML | 2
38 |  | Payment Gateway: Paypal, For India | 5
39 |  | Checkout: Shiiping according to address | 2
40 |  | Checkout: Payment method according to billing | 3
41 |  | Customer Login: HTML Integrate | 1
42 |  | Customer: Add edit, delete addresses | CMS Feature
43 |  | Customer: Order Summary | CMS Feature
44 |  | Customer Login: Complete Payment if Pending | 3
45 |  | Customer Login: Add options if custom option selected | 2
46 |  | Upload Product and inventory
47 |  | Wholesale Buyer Concept | 6
48 |  | Different Currency, Css, Banners on bases of IP address | 8
49 |  | Affiliate Module
50 | Testing | Backend, Frontend | 6
51 | Bug Fixing | Backend, Frontend | 3
52 | Launch site | Transfering site from development server to live server | 2
| Total(days) |  | 77
|  | Total Man Hours | 616
|  | Cost Estimation - (INR) | 184800
|  | Design Costing | 35000
|  | TOTAL Costing + Service Tax Additional | 219800